## Sheet1
Task | Start Date | End Date | Duration | Status
1.Project Planning and Setup | 2024-08-20 | 2024-08-27 | 5 days | Not Completed
1.1 Define Project Scope | 2024-08-20 | 2024-08-23 | 3 days | Not Completed
1.2 Set Up Development Environment | 2024-08-24 | 2024-08-26 | 2 days | Not Completed
2. Design Phase | 2024-08-27 | 2024-09-09 | 15 days | Not Completed
2.1 UI/UX Design | 2024-08-27 | 2024-09-01 | 4 days | Not Completed
2.2 Database Design | 2024-08-29 | 2024-09-03 | 5 days | Not Completed
2.3 System Architecture Design | 2024-09-03 | 2024-09-09 | 6 days | Not Completed
3. Development Phase | 2024-09-10 | 2024-09-30 | 20 days | Not Completed
3.1 User Registration | 2024-09-10 | 2024-09-14 | 4 days | Not Completed
3.2 Room Booking | 2024-09-12 | 2024-09-18 | 6 days | Not Completed
3.3 Booking Management | 2024-09-17 | 2024-09-25 | 8 days | Not Completed
3.4 Payment Processing | 2024-09-23 | 2024-09-27 | 4 days | Not Completed
3.5 Admin Dashboard | 2024-09-24 | 2024-09-30 | 6 days | Not Completed
3.6 Notifications and Alerts | 2024-09-24 | 2024-09-30 | 6 days | Not Completed
4. Testing Phase | 2024-10-01 | 2024-10-10 | 10 days | Not Completed
4.1 Unit Testing | 2024-10-01 | 2024-10-03 | 2 days | Not Completed
4.2 Integration Testing | 2024-10-03 | 2024-10-05 | 2 days | Not Completed
4.3 User Acceptance Testing | 2024-10-04 | 2024-10-10 | 6 days | Not Completed
5. Deployment Phase | 2024-10-09 | 2024-10-15 | 6 days | Not Completed
5.1 Deployment to Production | 2024-10-09 | 2024-10-14 | 5 days | Not Completed
5.2 Go Live | 2024-10-14 | 2024-10-15 | 1 day | Not Completed
6. Post-Deployment | 2024-10-14 | 2024-10-20 | 6 days | Not Completed
6.1 Monitoring and Support | 2024-10-14 | 2024-10-20 | 6 days | Not Completed
6.2 Bug Fixes | 2024-10-14 | 2024-10-20 | 6 days | Not Completed